# OSMC planning – Red October

Jan Brugård, MathCore Engineering AB

Jan.brugard@mathcore.com

Customer: 	OSMC

Version:	1.00

Date:		2010-09-09

# Goal

The goal for the Red October milestone is to focus work on issues that will

- Result in substantial speed-up of the flattening process

- Secure full Modelica 3.1 flattening support of those libraries that where fully supported in Modelica 2.1

This should be performed in a way that

- Minimizes risks of secondary effects on the kernel

- Minimizes the risk of not meeting the deadline 2010-10-15!

In order to accomplish this, issues meeting these criteria’s have been selected. Furthermore, when possible their time consumption has been roughly estimated. Based on this priorities has been set, and the tickets should be taken care of in the order of priority. If you encounter that an issue is possibly more complicated, risky, or has less impact than expected, then this should be discussed with the group to see if we need to re-priorities. Any issues outside the milestone should only be done if they are considered to be critical by Peter Fritzson.

# Flattening speed-up

In the table below 1 indicates the lowest impact, risk, and priority respectively.

| Description | Impact | Risk | Priority | Effort (superman) | CodeBeamer | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| Parsing of Modelica.Code class | 1 | 2 | 5 |  |  | Can be removed from the release. |
| Command switch, connection breaking | 5 | 2 | 5 | 1 | BUG-1268 |  |
| Parsing, using ANTLR3, building of AST | 2 | 2 | 4 | 3 | TSK-1266 | Has already been started, if the estimated effort i expected to be greater than the effort estimated by Adrian we should consider postponing this issue. |
| Parsing of empty expressions | 4 | 2 | 3 | 1 | BUG-1267 |  |
| Improved handling of inner/outer | 5 | 5 | 3 |  |  | Hard to set priority as the impact is very high, but the risk is also very high. Setting normal, we should discuss this more. |
| Do not check components that will be deleted/Overconstrained connection graph | 4 | 3 | 3 | 2-5 |  |  |
| DAE structure as a tree | 4 | 4 | 2 |  |  | This should only be done when less risky, higher prioririty issues have been secured |
| Streams | NA | 4 | 1 | 1 | TSK-1269 | this does not affect performance and is a new feature, therefore not high priority, but if there is time before the deadline this can be completed |
| re-enable string sharing in MetaModelica | check |  |  |  |  | Adrian needs to check the potential effect before we analyse this issue |
| Rewriteing default connection according to the specification | check | 4 |  | 3 |  | Adrian needs to check the potential effect before we analyse this issue |

| Description | Impact | Risk | Priority | Effort (superman) | CodeBeamer | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| Parsing of Modelica.Code class | 1 | 2 | 5 |  |  | Can be removed from the release. |
| Command switch, connection breaking | 5 | 2 | 5 | 1 |  |  |
| Parsing, using ANTLR3, building of AST | 2 | 2 | 4 | 3 |  | Has already been started, if the estimated effort i expected to be greater than the effort estimated by Adrian we should consider postponing this issue. |
| Parsing of empty expressions | 4 | 2 | 3 | 1 |  |  |
| Improved handling of inner/outer | 5 | 5 | 3 |  |  | Hard to set priority as the impact is very high, but the risk is also very high. Setting normal, we should discuss this more. |
| Do not check components that will be deleted/Overconstrained connection graph | 4 | 3 | 3 | 2-5 |  |  |
| DAE structure as a tree | 4 | 4 | 2 |  |  | This should only be done when less risky, higher prioririty issues have been secured |
| Streams | NA | 4 | 1 | 1 |  | this does not affect performance and is a new feature, therefore not high priority, but if there is time before the deadline this can be completed |
| re-enable string sharing in MetaModelica | check |  |  |  |  | Adrian needs to check the potential effect before we analyse this issue |
| Rewriteing default connection according to the specification | check | 4 |  | 3 |  | Adrian needs to check the potential effect before we analyse this issue |

# General Modelica 3.1 support

Several models that worked to check with Modelica 2.1 do not work after the switch to 3.1. The user would expect that anything that worked before will continue working, so they won’t be prepared to take a step buck in functionality just because they get 3.1, therefore these models need to be fixed. Below is a list of libraries with non-working models. A detailed list of models can be found in the Appendix, “OSMC CheckMSL-100906.xls”.

| Description | No. Of models affacted | Priority | CodeBeamer |
| --- | --- | --- | --- |
| Modelica.Blocks | 12 | 5 |  |
| Modelica.Electrical.Analog | 32 | 5 |  |
| Modelica.Math | 12 | 5 |  |
| MultiBody.Frames | 5 | 5 |  |
| MultiBody.Interfaces | 1 | 5 |  |
| MultiBody.Types | 1 | 5 |  |